## Project 1
Parameter | Notation | Formula | Test 1 | Test 2 | Test 3 | Test 4
Budget at Completion | BAC |  | 650000
Planned Budget | PV |  | 300000
Spent | AC |  | 326000
Cost Variance | CV | CV = PV - AC | -26000
Cost Performance Index | CPI | CPI = PV / AC | 0.92025
Estimate at Completion | EAC | EAC = BAC / CPI | 706333.3333
Variance at Completion | VAC | VAC = BAC - EAC | -56333.3333